Meeting Minutes 7_10

- Big picture: Come up with guidelines to propose to SSO, ASCO for endorsement, and ultimately work towards alignment with NCCN, NANETS, ASCRS

  - Nancy Baxter recommends we reach out to ASCRS now as will be difficult to align later if not correctly prepared

- Working towards educational improvement for CRS/HIPEC

- Working towards clinical trial coordination for PSM

Pathway update

- Please fill out Delphian survey

  - After this round is closed, we will have closed group meetings to discuss results and potential edits before circulating round 2

  - Planned to close 7/13/23

  - Small group workshops will work towards having medical oncology recommendations included in final recommendations, particularly for meso and appendix

Scoping/systematic review update

- Full text review to complete approximately 8/7/23

  - Data extraction + QA to complete over next two months

  - Metaanalyses to finish before October

- Updates by disease site

  - Colorectal KQs 1, 3 abstract screening complete; 2, 4, 5 in progress

  - Appendix abstract screening complete, full text to proceed over next 1-3 weeks

  - Single question groups: meso and NET abstracts complete, full text in process; MIS abstract screening partially complete; palliative KQs to be completed 2-3 weeks

- Concerns brought up by group about scoping review search methodology

  - Nancy Baxter: scoping reviews are not truncated systematic reviews; would like to clarify methodologies used – PSM internal group will plan to reach out separately

Education update

- Needs assessment in final phases between attendings and residents

- Canvas course being built up

Conference members would like Delphian round links to be sent out again.