Meeting Minutes 7_10
· Big picture: Come up with guidelines to propose to SSO, ASCO for endorsement, and ultimately work towards alignment with NCCN, NANETS, ASCRS
· Nancy Baxter recommends we reach out to ASCRS now as will be difficult to align later if not correctly prepared
· Working towards educational improvement for CRS/HIPEC
· Working towards clinical trial coordination for PSM
Pathway update
· Please fill out Delphian survey
· After this round is closed, we will have closed group meetings to discuss results and potential edits before circulating round 2
· Planned to close 7/13/23
· Small group workshops will work towards having medical oncology recommendations included in final recommendations, particularly for meso and appendix
Scoping/systematic review update
· Full text review to complete approximately 8/7/23
· Data extraction + QA to complete over next two months
· Metaanalyses to finish before October
· Updates by disease site
· Colorectal KQs 1, 3 abstract screening complete; 2, 4, 5 in progress
· Appendix abstract screening complete, full text to proceed over next 1-3 weeks
· Single question groups: meso and NET abstracts complete, full text in process; MIS abstract screening partially complete; palliative KQs to be completed 2-3 weeks
· Concerns brought up by group about scoping review search methodology
· Nancy Baxter: scoping reviews are not truncated systematic reviews; would like to clarify methodologies used – PSM internal group will plan to reach out separately 
Education update
· Needs assessment in final phases between attendings and residents
· Canvas course being built up
Conference members would like Delphian round links to be sent out again.
